## Test Plan
TS ID | TC Name | Action/Description | Expected Results | Status | Comments | Developer | Date Tested | Tester
| VRV-1 | Website Testing
TC1.1 | Verify Homepage Load | Navigate to the website’s homepage. | Homepage loads successfully with all key elements (logo, navigation, hero section). | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-22 | Donice Ubaru
TC1.2 | Navigation Bar Functionality | Ensure all top-level navigation links are clickable and direct to the correct page | All navigation links should direct users to the appropriate section without any broken links | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-23 | Donice Ubaru
TC1.3 | Validate Lead Form Display | Navigate to a lead generation form page. | Lead form is visible and properly aligned on the page. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-24 | Donice Ubaru
TC1.4 | Test Form Submission (Valid) | Fill out the lead generation form with valid data and submit. | Form submits successfully, confirmation message appears, and data is stored. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-25 | Donice Ubaru
TC1.5 | Test Form Submission (Invalid) | Leave mandatory fields blank or input invalid data (e.g., wrong email format). | Form does not submit; error messages are displayed for the invalid fields. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-26 | Donice Ubaru
TC1.6 | Verify Form Auto-Response | Submit the lead form with valid data. | Auto-response email is sent to the provided email address. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-27 | Donice Ubaru
TC1.7 | Test Mobile Responsiveness | Open the lead form page on a mobile device or emulator. | Form and page are responsive, with all elements properly aligned. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-28 | Donice Ubaru
TC1.8 | Test Thank You Page Redirect | Submit the form and check for redirection to a thank-you page. | User is redirected to a thank-you page after successful submission. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-29 | Donice Ubaru
TC1.9 | Validate Lead Tracking | Submit the form and verify if the lead is logged in the backend CRM or database. | Lead details are correctly captured and saved in the CRM/database. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-30 | Donice Ubaru
TC1.10 | Image Optimization | Test if all images on the homepage and subpages are optimized for fast loading without compromising quality | Images should load quickly (within 2 seconds) and be clear; lazy loading should be enabled | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-10-31 | Donice Ubaru
TC1.11 | Accessibility Compliance | Test the website for accessibility features (ARIA labels, keyboard navigation, screen reader compatibility, contrast ratio) | Website should comply with WCAG 2.1 standards; all elements should be accessible via keyboard navigation and screen readers | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-01 | Donice Ubaru
TC1.12 | Social Media Links | Verify the functionality of all social media icons (LinkedIn, Twitter, Facebook) in the footer section | All social media icons should redirect users to the correct social media pages without errors | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-02 | Donice Ubaru
TC1.13 | Secure Browsing (HTTPS) | Test if the website is secure by checking the HTTPS protocol and verifying that SSL certificates are valid and up-to-date | The website should load using HTTPS, and the SSL certificate should be valid | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-03 | Donice Ubaru
TC1.14 | Error Page Handling (404, 500) | Test error handling by navigating to non-existent or broken URLs | Custom error pages should appear (404 for non-existent pages, 500 for server errors), with options to return to the homepage | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-04 | Donice Ubaru
TC1.15 | Cross-Browser Compatibility | Test website functionality across different browsers (Chrome, Safari, Firefox, Edge) | Website should display and function correctly across all major browsers without layout issues | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-05 | Donice Ubaru
TC1.16 | Content Load Test | Verify that content such as text, images, and videos load properly under varying network conditions (Wi-Fi, 4G, 3G) | All content should load without delays on both high and low-speed networks | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-06 | Donice Ubaru
TC1.17 | Cookie Consent Banner | Test the functionality of the cookie consent banner by accepting, declining, and customizing cookie settings | The cookie consent banner should function correctly, and user preferences should be applied | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-07 | Donice Ubaru
TC1.18 | SEO Metadata | Check if the website's metadata (titles, descriptions, alt text for images) is properly configured for SEO | All pages should have appropriate titles, meta descriptions, and image alt tags for SEO | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-08 | Donice Ubaru
TC1.19 | Test Analytics Integration | Submit a form while monitoring analytics tools (e.g., Google Analytics, Netcore, Microsoft Dynamics). | Form submissions trigger events or goals as configured in analytics. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-09 | Donice Ubaru
TC1.20 | Performance under Load | Simulate heavy user traffic to test the website’s performance under load (using tools like Apache JMeter) | The website should maintain acceptable load times and not crash under heavy user traffic | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-10 | Donice Ubaru
TC1.21 | Verify Social Sharing Links | Click on any social sharing links available on the thank-you page or form page. | Social media pages open correctly in new tabs. | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2024-11-11 | Donice Ubaru
TC1.22 | Multi-Country Support | Test if the website offers multi-language support and verify proper content if available (English and French) | Website content should be correctly translated into all supported countries | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2025-01-28 | Donice Ubaru
TC1.23 | Blog Update | Visit the blog page and look for a published/updated date. | No broken links should be found; all links should navigate to the correct destination | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2025-02-18 | Clement Bazuaye
TC1.23 | NCP Date Update | Visit ncp page and check for the correct date for the campaign | Page displays correct date for the extended campaign | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2025-02-18 | Clement Bazuaye
TC1.23 | News/Article Update | Check if the new articles uploaded on Contenful preview on the my verveworld website. | Page displays as expected | Pass |  | Kelvin Anwuzia & Clement Bazuaye | 2025-03-20 | Clement Bazuaye
TC1.24 | News/Article Update | Check if the new articles uploaded on Contenful preview on the my verveworld website. | Page displays as expected | Pass | https://interswitch.atlassian.net/browse/VMW-20 | Kelvin Anwuzia & Clement Bazuaye | 2025-05-06 | Clement Bazuaye
TC1.25 | Runtime server, privacy policy and global partners update | Check if the new articles uploaded on Contenful preview via endpoint call and confirm the new privacy policy has been updated | Page displays as expected | Pass | https://interswitch.atlassian.net/browse/VMW-20 | Kelvin Anwuzia & Clement Bazuaye | 2025-05-06 | Clement Bazuaye
TC1.26 | Deploy cookie consent policy script | Check if cookie policy banner previews on site | Page displays as expected | Pass | https://interswitch.atlassian.net/browse/VMW-24 | Kelvin Anwuzia & Clement Bazuaye | 2025-05-12 | Clement Bazuaye
TC1.26 | Deploy new privacy policy | Check if privacy policy has been updated | Page displays as expected | Pass | https://interswitch.atlassian.net/browse/VMW-24 | Kelvin Anwuzia & Clement Bazuaye | 2025-05-29 | Clement Bazuaye
TC1.27 | Deployed new blogpost article | Check if the article updates shows perfectly | Page displays as expected | Pass | https://interswitch.atlassian.net/browse/VMW-28 | Kelvin Anwuzia & Clement Bazuaye | 2025-02-06 | Donice Ubaru
TC1.28 | Deployed new blogpost article - Verve African Expansion | Check if the article updates shows perfectly | Page displays as expected | Pass | https://interswitch.atlassian.net/browse/VMW-29 | Kelvin Anwuzia & Clement Bazuaye | 2025-07-07 | Clement Bazuaye
TC1.28 | Deployed new blogpost articles | Check if the article updates shows perfectly | Page displays as expected | Pass | https://interswitch.atlassian.net/browse/VMW-31 | Kelvin Anwuzia & Clement Bazuaye | 19/7/2025 | Clement Bazuaye
TC1.28 | Deployed the Verve Goodlife 6.0 | Check if Verve Goodlife 6.0 appears perfectly. | Page displays as expected | Pass | https://interswitch.atlassian.net/browse/VMW-33 | Kelvin Anwuzia & Clement Bazuaye | 23/7/2025 | Clement Bazuaye
TC1.28 | Vervelife 8.0 Registration Landing Page | Check if Vervelife 8.0 appears perfectly and if the registrations captures as expected | Page displays as expected and registration works as expected | Pass | https://interswitch.atlassian.net/browse/VMW-38 | Kelvin Anwuzia & Clement Bazuaye | 2025-04-08 | Clement Bazuaye
TC1.28 | Vervelife 8.0 and Goodlife 6.0 Content Update | Check if Vervelife 8.0 and Goodlife 6.0 appears propely | Page displays as expected and registration works as expected | Pass | https://interswitch.atlassian.net/browse/VMW-39 | Kelvin Anwuzia & Clement Bazuaye | 2025-05-08 | Clement Bazuaye
TC1.28 | Vervelife 8.0 | Check if Vervelife 8.0 appears propely | Page displays as expected and registration works as expected | Pass | https://interswitch.atlassian.net/browse/VMW-42 | Kelvin Anwuzia & Clement Bazuaye | 2025-06-08 | Clement Bazuaye
TC1.28 | Content Update for Goodlife, Vervelife & Homepage | Check if platform appears propely | Page displays as expected and registration works as expected | Pass | https://interswitch.atlassian.net/browse/VMW-43 | Kelvin Anwuzia & Clement Bazuaye | 18/8/2025 | Clement Bazuaye
TC1.28 | Content Update for Goodlife, | Check if platform appears propely | Page displays as expected and registration works as expected | Pass | https://interswitch.atlassian.net/browse/VMW-48 | Donice Ubaru | 21/8/2025 | Clement Bazuaye