## Prioritized
SN | Enhancement/Fix/Technical debt to be worked on
1 | Review View Modals vis a vis information displayed for card/artwork/decal/decal requests/whitelists for pending, approved and rejected views
2 | Billing Statement lines - make lines more user friendly - allow copy and paste into the fields, tab to navigate from one field to another, editing from anywhere the cursor is positioned as opped to the end of the text
3 | Pop-Up Confirmation before creation of user guide
4 | View option for user guide
5 | Tab to view deleted institutions and users
6 | Update Enable/Disable organization endpoints to accept comments
7 | Fix single enable/disable organization endpoints to disable/enable all users linked to the organization
8 | Review processes and update confirmation actions where applicable
9 | Update swagger api documentation

## Sheet1
SN | Enhancement/Fix/Technical debt to be worked on | Why is this fix needed? | Description of the improvement this fix will bring | Name of Reporter | BE DEV Breakdown/Estimate | FE DEV Breakdown/Estimate | QA Estimate | Expectations
1 | Review View Modals vis a vis information displayed for card/artwork/decal/decal requests/whitelists for pending, approved and rejected views | More streamlined/meaningful information based on the status of the request | Improved UX | Ogechi | - Update all queries to fetch the updated information on card entity. - 1 - Update all queries to fetch the updated information on artwork entity. - 1 - Update all queries to fetch the updated information on decal entity. - 1 - Update all queries to fetch the updated information on decal request entity. - 1 - Update all queries to fetch the updated information on whitelist entity. - 1 - Update the existing service to capture the new information from the updated query. -0.5 - Update the view model for each entity. – 0.5 6 days (Corporate and Admin) - Paul | - Modification of Card, Artwork, Decal, Request, Whitelist (Pending, Approved & Rejected) modal "Admin & Coorperate Portal" ( 2 days) - Jonathan | 3 | BE- APIs should be ready by 21st December Morning FE- UI will be worked on first , integration will be done by 27-28th Dec
2 | Pop-Up Confirmation before creation of user guide | A pop-up notification can be introduced to avoid uploading an erroneous file. | 1st level validation before upload of user guides | Ogechi |  | Addition of Pop-Up Confirmation before creation of user guide - (1 day) - Christopher | 0.5 | Should be ready by 22nd Dec
3 | View option for user guide | A view-only feature can be introduced as a check for admin to be sure that the right file is being uploaded. | 2nd level validation before upload of user guides | Ogechi | - Provide an endpoint to fetch and download a guide that has already been uploaded. - 2 2 Days - Idris | Addition of View option to the Action column for user guide to preview and download - (2 days) - Christopher | 2 | Should be ready by 22nd Dec
4 | Tab to view deleted institutions and users | To keep track of institutions and users that have been deleted and the reason for the deletion | Reference point for the scheme team | Ogechi | - Provide an endpoint to fetch all deleted institutions. - 2 - Provide an endpoint to fetch all deleted users per organization. - 2 4 Days - Idris | Addition of Deleted Tab to view deleted institutions- (2 days) - Jonathan | 3 | BE- APIs should be ready by 21st December Morning FE- UI will be worked on first , integration will be done by 27-28th Dec
5 | Update Institution field on Billing Statement to enter text and match entry | To enable searching for/filtering out required institution seamless | Improved UX | Ogechi |  | RESOLVED
6 | Billing Statement lines - make lines more user friendly - allow copy and paste into the fields, tab to navigate from one field to another, editing from anywhere the cursor is positioned as opped to the end of the text | For better UX | Easy navigation from one field to another, easier way to edit entries in the field and allowing users to paste copied data in the fields | Ogechi |  | Modification of Billing Statement lines - (7days) - 1. enable copy and paste in the billing lines(2days). 2. Enable onkey editing in the billing lines(2.5days) . 3 Tap enalble in the billing lines(2.5days)-Christopher |  | Should be ready by 20th Dec
7 | Update swagger api documentation | To remove obsolete endpoints and update request payloads to capture what is needed for the endpoint and all possible responses | Up-to-date API documentation |  | - Remove all obsolete endpoints.
8 | Update Enable/Disable organization endpoints to accept comments |  |  | Idris Osinfade | - Provide an endpoint to enable organization and give room for comments. - 1 - Provide an endpoint to disable organization and give room for comments. - 1 - Provide an endpoint to bulk enable organization and give room for comments. - 1 - Provide an endpoint to bulk disable organization and give room for comments. - 1 4 Days - Idris | Modification of organization actions to accept comments - 3 days Jonathan | 4 | BE- APIs should be ready by 2nd Jan FE- UI work will start first , but due to the work load will be completed alongside the integration
9 | Fix single enable/disable organization endpoints to disable/enable all users linked to the organization |  |  |  | - Create a service to enable / disable all the users belonging to an organization when enabling/disabling the organization.
10 | Update the createBilling and Preview page to show loading first before rendering the pages | For better UX | Improved UX | Christopher Ushie |  | RESOLVED
11 | Review processes and update confirmation actions where applicable |  |  | Jonathan Alabi |  | Addition of Confirmation modal on institution page in Admin Portal - 3 day - Jonathan | 1 | FE-Should be ready by 15th Dec
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Idris Osinfade will you need to update the endpoint to view deleted users for the organization
Note on G12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Jonathan Alabi I don't think this is the only place a confirmation pop-up is missing. You should go through all the features on admin and corporate and ensure everything is captured. I know it's not on Reports, Requests, VMMR etc Reply: User Permissions, Contact Details, Users on Corporate